## Sheet1
Story | Task | Estimate min (hr) | Estimate max (hr) | Actual | Comment
SprintSync Backend | Project Setup & Initial Configuration | 1 | 3 |  | Initial project structure, dependency setup, and basic config
SprintSync Backend | Database Models & Schema Design | 2 | 4 |  | SQLAlchemy models, Alembic migrations, and database configuration
SprintSync Backend | Authentication System Implementation | 3 | 5 |  | JWT auth, password hashing, token management, and security
SprintSync Backend | Core API Endpoints (Tasks) | 2 | 4 |  | CRUD operations for tasks with proper authorization
SprintSync Backend | User Management Endpoints | 2 | 3 |  | User CRUD operations with admin permissions
SprintSync Backend | AI Integration (Groq API) | 3 | 6 |  | AI suggestion feature with proper error handling and fallbacks
SprintSync Backend | Exception Handling & Error Management | 1 | 2 |  | Custom exception classes and global error handler
SprintSync Backend | Testing Suite (Unit & Integration) | 4 | 8 |  | Comprehensive test coverage for all endpoints and features
SprintSync Backend | Docker Configuration | 1 | 2 |  | Dockerfile and docker-compose for local development
SprintSync Backend | Deployment Configuration (Render) | 2 | 4 |  | Production deployment setup, build scripts, and environment config
SprintSync Backend | CORS & Middleware Configuration | 1 | 2 |  | Cross-origin setup and request logging middleware
SprintSync Backend | API Documentation & Code Quality | 2 | 3 |  | Code cleanup, comments, and final polishing